## Jira Tasks
Epic | Story | Task | Priority | Sprint | Status
Setup | Project Initialization | Initialize MERN repositories and folder structure | High | Sprint 1 | To Do
Authentication | JWT Auth | Register/Login APIs | High | Sprint 1 | To Do
Authentication | RBAC | Role middleware | High | Sprint 1 | To Do
Products | CRUD | Product CRUD APIs | High | Sprint 2 | To Do
Products | Frontend | Product pages | High | Sprint 2 | To Do
Customers | CRUD | Customer management | Medium | Sprint 2 | To Do
Suppliers | CRUD | Supplier management | Medium | Sprint 2 | To Do
Sales | Orders | Sales Order module | High | Sprint 3 | To Do
Purchase | Orders | Purchase Order module | High | Sprint 3 | To Do
Inventory | GRN | Goods Receipt Note | High | Sprint 3 | To Do
Invoices | PDF | Invoice generation | High | Sprint 4 | To Do
Dashboard | Analytics | Charts & metrics | Medium | Sprint 4 | To Do
Testing | QA | Unit and integration tests | Medium | Sprint 5 | To Do
Deployment | Release | Deploy to Render/Vercel | High | Sprint 5 | To Do